* Describe staff change and increased demands
* No change in tech capabilities
* Tribal partnerships
* Qapp draft and EPA review
* AQWMS transition

Hi Jessica,

I wanted to touch base with you regarding the 270 day sufficiency report that we have due on Aug 31.

I am considering requesting a revision to the project schedule. I'll provide the details forthcoming, but beforehand I just wanted to check to see if you had thoughts on what the implications and consequences of formally requesting to modify the project schedule.

The project is going well overall, but we are behind schedule. The reason for this is that we've had several major staff transitions in the last several months at our small organization, which has led to me temporarily taking on many unplanned responsibilities.

Since I'm the primary staff involved with this project, there hasn't been a change in technical capacity, and we are still planning to produce the same deliverables. The progress we've made is great progress, and I'm particularly excited about some new partners we've gained as part of sharing this work with our community. However, I want to be transparent in explaining where we’re at, which is not quite as far along yet as originally planned for this date.

I’ll provide the details formally soon. Please be in touch if I can answer any additional questions, I am happy to talk further anytime.

Thank you for your time. All the best,

Ben